## JaetRobi Project Gantt
Phase | Task Name | Start Date | End Date | Status | 22.04. | 23.04. | 24.04. | 25.04. | 26.04. | 27.04. | 28.04. | 29.04. | 30.04. | 01.05. | 02.05. | 03.05. | 04.05. | 05.05. | 06.05. | 07.05. | 08.05. | 09.05. | 10.05. | 11.05. | 12.05. | 13.05. | 14.05. | 15.05. | 16.05. | 17.05. | 18.05. | 19.05. | 20.05. | 21.05. | 22.05. | 23.05. | 24.05. | 25.05. | 26.05. | 27.05. | 28.05. | 29.05. | 30.05. | 31.05. | 01.06. | 02.06. | 03.06. | 04.06. | 05.06. | 06.06. | 07.06. | 08.06. | 09.06. | 10.06. | 11.06. | 12.06. | 13.06. | 14.06. | 15.06. | 16.06. | 17.06. | 18.06. | 19.06. | 20.06. | 21.06. | 22.06. | 23.06. | 24.06. | 25.06. | 26.06. | 27.06. | 28.06. | 29.06. | 30.06. | 01.07. | 02.07. | 03.07. | 04.07. | 05.07. | 06.07. | 07.07. | 08.07. | 09.07. | 10.07. | 11.07. | 12.07. | 13.07. | 14.07. | 15.07. | 16.07. | 17.07. | 18.07. | 19.07. | 20.07. | 21.07. | 22.07. | 23.07. | 24.07. | 25.07. | 26.07. | 27.07. | 28.07. | 29.07.
Phase 0 | Requirements Definition & Client Consultation | 2026-04-22 | 2026-04-24 | Done
Phase 0 | Finalize Specs (Accuracy, Budget, Code Standards) | 2026-04-24 | 2026-04-25 | Done
Phase 1 | Connect TLV493D to Raspberry Pi 5 | 2026-04-26 | 2026-04-27 | Done
Phase 1 | Verify Sensor Data Output Format | 2026-04-28 | 2026-04-29 | Done
Phase 1 | Implement Trigonometric Math (Yaw, Pitch, Roll) | 2026-04-30 | 2026-05-02 | Done
Phase 2 | Adhesive Mounting & Orientation Testing | 2026-05-03 | 2026-05-05 | Done
Phase 2 | Develop SensorPoller Class (Threading, Polling Rate) | 2026-05-06 | 2026-05-08 | Done
Phase 2 | Implement EMA Filter & Threadsafe Output | 2026-05-09 | 2026-05-10 | Done
Phase 3 | Design 3D Clip-on Mounts (Non-magnetic, < 5€) | 2026-05-11 | 2026-05-20 | Done
Phase 3 | Print & Iterate Mounting Solutions | 2026-05-21 | 2026-05-31 | Done
Phase 3 | Manual Angle Calibration Measurements | 2026-06-01 | 2026-06-14 | Done
Phase 3 | Build Lookup Tables & Fit Characteristic Curves | 2026-06-15 | 2026-06-25 | Done
Phase 4 | Develop Spatial Magnetic Field Gradient Tracking | 2026-06-26 | 2026-07-10 | Done
Phase 4 | Implement Optimization Function | 2026-07-11 | 2026-07-21 | Done
Phase 4 | Record Ground Truth Trajectories | 2026-07-01 | 2026-07-06 | Done
Phase 4 | Train & Evaluate Neural Network | 2026-07-01 | 2026-07-08 | Done
Refinements | Code Refactoring & Testing | 2026-07-22 | 2026-07-27 | To Do
Refinements | Write Final Documentation for Deployment | 2026-07-15 | 2026-07-29 | To Do
Refinements | Final Bug Fixes & Refinements | 2026-07-22 | 2026-07-29 | To Do
Submission | Final Project Submission | 2026-07-29 | 2026-07-29 | Milestone